## Slide 1: Retail System Implementation Plan
By: Yamil Diaz

## Slide 2: Project scenario
I propose a new Retail Information System for a store chain that is still using outdated software
The new system would support daily retail operations such as:
  order processing
  inventory updates
  Reporting
  customer service.
The goal is to replace slow and disconnected processes with one system that improves accuracy, speed, and decision-making.

## Slide 3: Chosen methodology
Agile methodology with incremental releases
I think Agile fits retail well because retail environments change quickly
Agile is a good choice here because the team can release the system in smaller parts, such as:
  inventory management
  sales
  Checkout
  Reporting
  customer account features
This lowers risk compared to trying to do everything at once. At the same time, I would still keep strong documentation, test plans, and project controls

## Slide 4: Planning objectives and strategies
The planning objectives include:
replacing manual and outdated retail processes
Improving inventory accuracy and order processing speed
reducing duplicate data entry and reporting delays
supporting future growth and scalability
training users so the system is accepted and used correctly
completing implementation with minimal disruption to store operations.
The strategies to meet these objectives include:
creating a work breakdown structure (WBS) with clearly defined tasks and durations
using a Gantt chart to track planned and actual progress
monitor task dependencies and the critical path so delays are identified early
Hold regular status meetings and use written progress reports
Include risk ownership, probability, impact, and contingency planning
Include training, testing, and data conversion early instead of leaving them for the end.

## Slide 5: Installation strategy
phased installation approach so that it is a step-by-step rollout that is more gradual and manageable
A phased approach is best for retail because a retail system usually has separable modules, like inventory, sales processing, customer orders, and reporting.
This is safer than direct cutover and cheaper than full parallel operation.
Installation Schedule
Set up a production environment.
Confirm system configuration and network readiness.
Complete final backup of old data/system.
Roll out the inventory module first.
Monitor performance and user issues.
Roll out sales/order processing module.
Roll out reporting/dashboard module.
Compare outputs and verify transactions.
Provide floor support and help desk assistance.
Retire legacy functions after successful validation.

## Slide 6: Data migration plan and ETL flow
Extract
pull product records
inventory quantities
customer records
sales history
supplier data
pricing tables
Transform
remove duplicates
correct errors
standardize product names and codes
clean customer contact records
map old fields to new system fields
Load
load cleansed data into the new retail database
validate totals, counts, and sample records
compare migrated output with expected results
Migration controls
perform data profiling and cleansing first
use field mapping checks
run a pilot migration before full rollout
test for completeness and accuracy after loading

## Slide 7: Test cases
Test Case 1: Login validation
Test case ID: TC-01 Objective: ensure valid users can log in and invalid users are blocked. Input: valid username/password and invalid username/password combinations. Steps:
Open login page.
Enter valid credentials.
Click sign in.
Repeat with invalid credentials. Expected result:
valid user enters dashboard successfully
invalid user gets error message and no access
Test Case 2: Sales transaction processing
Test case ID: TC-02 Objective: verify that a completed sale updates sales totals and inventory correctly. Input: one product with known inventory count and sale quantity. Steps:
Log in as cashier.
Scan/select product.
Complete sale.
Check receipt, sales log, and updated inventory count. Expected result:
sale is saved successfully
receipt is generated
inventory count decreases correctly
transaction appears in reporting records

## Slide 8: Debugging and Handling Errors
Strategies include:
  maintaining detailed error logs for login
  transactions, and inventory updates
  categorizing issues by severity
  fixing critical issues first
  retesting after every fix
  using friendly user messages instead of system crash messages
  keeping rollback procedures for failed module releases
  tracking recurring errors to identify root causes.

## Slide 9: Data Quality Issues
Possible data quality issues in retail
  duplicate customer records
  outdated pricing
  missing supplier information
  inconsistent product naming
  inventory counts that do not match reality
  incomplete sales history
Data cleansing strategies
  profile source data before migration
  remove duplicates
  correct obvious errors
  standardize formats and codes
  map old fields to new fields carefully
  validate totals and sample records after migration

## Slide 10: Conversion Method Testing and Validation Steps
I would use an automated and phased conversion method
This makes sense for retail because there can be a high volume of products, customers, and sales records.
Doing this manually would be too slow and could result in errors.
A phased conversion also fits the phased installation strategy, which reduces overall business risk.
compare old and new record counts
validate sample customer, product, and sales records
verify inventory totals
check pricing and tax fields
run transaction tests on migrated data
confirm reports produce correct output
get business user confirmation on sample results
document issues and rerun corrections if needed

## Slide 11: key success factors and post-implementation review criteria
Key success factors
project stays within cost, scope, and time targets
data migration is accurate and complete
users are trained and ready
critical defects are resolved before go-live
installation causes limited disruption
documentation is updated and usable
Post-implementation review criteria
system uptime after go-live
accuracy of inventory and transaction data
user satisfaction and training feedback
number and severity of post-go-live issues
speed of order processing/report generation
whether the system meets the original business objective

## Slide 12: lessons learned
A big lesson from this project is that implementation is not just about installing software. It also depends on project management, testing, data quality, user readiness, and documentation. For future implementations, continuous improvement should include:
updating training materials with each release
revising documentation when features change
reviewing defect trends
gathering user feedback after each rollout phase
improving future schedules using lessons from this project